## Setup
Enter the name of the Initiative being tracked in this workbook: | Sub - (Sept) Release
|  |  | 1 | Sunday
Enter the Sprint Ending date of the first Contributing Sprint: | 2018-04-16 | Monday, April 16, 2018 | 2 | Monday
|  |  | 3 | Tuesday
Enter the total number of Story Points estimated by the Team for this Initiative: | 1300 |  | 4 | Wednesday
|  |  | 5 | Thursday
Enter the Sprint Ending date whereupon you hope this Initiative will complete: | 2018-10-01 | Monday, October 01, 2018 | 6 | Friday
Sprint Duration (# of days in sprint): | 7
|  |  | 7 | Saturday

## Contribution Tracking
| Sprint | Per-Sprint Contribution to Sub - (Sept) Release: | Average Velocity (last 3 sprints) | Target Velocity | Initiative Content Scope Δ | Total Scope Remaining | # for Calculating Contributrion Needed | Per Sprint Contribution Needed to Meet Release Date | Product Owner Notes
| 2018-04-16 | 19 | 24 | 35 |  | 1300 | 1 | 54.1667 |  | Sprint 26
| 2018-04-23 | 37 | 21 | 35 |  | 1263 | 2 | 54.913 |  | Sprint 27
| 2018-04-30 | 44 | 33.3333 | 35 |  | 1219 | 3 | 55.4091 |  | Sprint 28
| 2018-05-07 | 27 | 36 | 45 |  | 1192 | 4 | 56.7619 |  | Sprint 29
| 2018-05-14 | 36 | 35.6667 | 45 |  | 1156 | 5 | 57.8 |  | Sprint 30
| 2018-05-21 | 50 | 37.6667 | 55 |  | 1106 | 6 | 58.2105 |  | Sprint 31
| 2018-05-28 | 64 | 50 | 55 |  | 1042 | 7 | 57.8889 |  | Sprint 32A
| 2018-06-04 | 51 | 55 | 45 |  | 991 | 8 | 58.2941 |  | Sprint 32B
| 2018-06-11 | 52 | 55.6667 | 45 |  | 939 | 9 | 58.6875
| 2018-06-18 | 57 | 53.3333 | 45 |  | 882 | 10 | 58.8
| 2018-06-25 | 54 | 54.3333 | 45 |  | 828 | 11 | 59.1429
| 2018-07-02 | 50 | 53.6667 | 45 |  | 778 | 12 | 59.8462
| 2018-07-09 | 62 | 55.3333 | 55 |  | 716 | 13 | 59.6667
| 2018-07-16 | 57 | 56.3333 | 65 |  | 659 | 14 | 59.9091
| 2018-07-23 | 66 | 61.6667 | 65 |  | 593 | 15 | 59.3
| 2018-07-30 | 59 | 60.6667 | 65 |  | 534 | 16 | 59.3333
| 2018-08-06 | 66 | 63.6667 | 65 |  | 468 | 17 | 58.5
| 2018-08-13 | 65 | 63.3333 | 65 |  | 403 | 18 | 57.5714
| 2018-08-20 | 64 | 65 | 65 |  | 339 | 19 | 56.5
Current>> | 2018-08-27 | 61 | 63.3333 | 65 |  | 278 | 20 | 55.6
| 2018-09-03 | [5 empty] | 21 | 55.6
| 2018-09-10 | [5 empty] | 22 | 55.6
| 2018-09-17 | [5 empty] | 23 | 55.6
| 2018-09-24 | [5 empty] | 24 | 55.6
| 2018-10-01 | [5 empty] | 25 | 55.6
| 2018-10-08 |  |  | 0 |  | -- | 26 | 55.6
| 2018-10-15 |  |  |  |  | -- | 27 | 55.6
| 2018-10-22 |  |  |  |  | -- | 28 | 55.6
| 2018-10-29 |  |  |  |  | -- | 29 | 55.6
| 2018-11-05 |  |  |  |  | -- | 30 | 55.6
| 2018-11-12 |  |  |  |  | -- | 31 | 55.6
| 2018-11-19 |  |  |  |  | -- | 32 | 55.6
| 2018-11-26 |  |  |  |  | -- | 33 | 55.6
| 2018-12-03 |  |  |  |  | -- | 34 | 55.6
| 2018-12-10 |  |  |  |  | -- | 35 | 55.6
| 2018-12-17 |  |  |  |  | -- | 36 | 55.6
| 2018-12-24 |  |  |  |  | -- | 37 | 55.6
| 2018-12-31 |  |  |  |  | -- | 38 | 55.6
| 2019-01-07 |  |  |  |  | -- | 39 | 55.6
| 2019-01-14 |  |  |  |  | -- | 40 | 55.6
| 2019-01-21 |  |  |  |  | -- | 41 | 55.6
| 2019-01-28 |  |  |  |  | -- | 42 | 55.6
| 2019-02-04 |  |  |  |  | -- | 43 | 55.6
| 2019-02-11 |  |  |  |  | -- | 44 | 55.6
| 2019-02-18 |  |  |  |  | -- | 45 | 55.6
| 2019-02-25 |  |  |  |  | -- | 46 | 55.6
| 2019-03-04 |  |  |  |  | -- | 47 | 55.6
| 2019-03-11 |  |  |  |  | -- | 48 | 55.6
| 2019-03-18 |  |  |  |  | -- | 49 | 55.6
| 2019-03-25 |  |  |  |  | -- | 50 | 55.6
| 2019-04-01 |  |  |  |  | -- | 51 | 55.6
| 2019-04-08 |  |  |  |  | -- | 52 | 55.6
Note on F2: Scott Downey: If the total scope of work required for this Initiative increases, enter the total of all Story Point estimates for all increases in requirements in the cell corresponding to the Sprint in which the increase was decided, discovered or otherwise occurred. If the Product Owner removes requirements from the total Initiative's Scope during a Sprint, enter the total Story Point estimates for all removed requirements as a negative number (e.g. -34) in the cell corresponding to the Sprint in which they were removed. NOTE: Do not "Scope Reduce" each Sprint when the Team completes work. Report completed work for this Initiative by totalling the Original Estimates of the work achieved toward the Initiative in each Sprint and enter it in the Contribution column beside that Sprint's ending date.

## Calc (hidden)
| Contribution Rows: | 20 | Plot: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | --
| Velocity Rows: | 21 | Sprint #: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
| Yesterday's Weather: | 61 | Period: | Launch | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08
| 3-Sprint Rolling Average Contribution: | 63 | Progress: | 1300 | 1281 | 1244 | 1200 | 1173 | 1137 | 1087 | 1023 | 972 | 920 | 863 | 809 | 759 | 697 | 640 | 574 | 515 | 449 | 384 | 320 | 259 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 3-Sprint Rolling Average Velocity: | 65 | Yesterday's Weather: | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 259 | 207.2 | 155.4 | 103.6 | 51.8 | -1.4211e-14 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Average Contribution: | 52 | Rolling 3 Sprint Avg: | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 259 | 207.2 | 155.4 | 103.6 | 51.8 | -1.4211e-14 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Average Velocity: | 52 | Total Average Contribution: | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 259 | 207.2 | 155.4 | 103.6 | 51.8 | -1.4211e-14 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Original Estimate: | 1300 | Original Goal: | 1300 | 1248 | 1196 | 1144 | 1092 | 1040 | 988 | 936 | 884 | 832 | 780 | 728 | 676 | 624 | 572 | 520 | 468 | 416 | 364 | 312 | 260 | 208 | 156 | 104 | 52 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Goal Date: | 2018-10-01
| Goal Number of Sprints: | 25 | Max | 1300 | 1256.6667 | 1213.3333 | 1170 | 1126.6667 | 1083.3333 | 1040 | 996.6667 | 953.3333 | 910 | 866.6667 | 823.3333 | 780 | 736.6667 | 693.3333 | 650 | 606.6667 | 563.3333 | 520 | 476.6667 | 433.3333 | 390 | 346.6667 | 303.3333 | 260 | 216.6667 | 173.3333 | 130 | 86.6667 | 43.3333 | 7.1054e-14 | -43.3333 | -86.6667 | -130 | -173.3333 | -216.6667 | -260 | -303.3333 | -346.6667 | -390 | -433.3333 | -476.6667 | -520 | -563.3333 | -606.6667 | -650 | -693.3333 | -736.6667 | -780 | -823.3333 | -866.6667 | -910 | -953.3333
| Current Sprint: | 2018-08-27 | Min | 1300 | 1235 | 1170 | 1105 | 1040 | 975 | 910 | 845 | 780 | 715 | 650 | 585 | 520 | 455 | 390 | 325 | 260 | 195 | 130 | 65 | 0 | -65 | -130 | -195 | -260 | -325 | -390 | -455 | -520 | -585 | -650 | -715 | -780 | -845 | -910 | -975 | -1040 | -1105 | -1170 | -1235 | -1300 | -1365 | -1430 | -1495 | -1560 | -1625 | -1690 | -1755 | -1820 | -1885 | -1950 | -2015 | -2080
| Total Scope Change: | 0
| Current Balance: | 259 | Full Velocity Applied | 1300 | 1235 | 1170 | 1105 | 1040 | 975 | 910 | 845 | 780 | 715 | 650 | 585 | 520 | 455 | 390 | 325 | 260 | 195 | 130 | 65 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Sprints to Plot: | 31
Projections | Yesterday's Weather: | 2018-10-01 | Scope Changes | 35 | 35 | 35 | 45 | 45 | 55 | 55 | 45 | 45 | 45 | 45 | 45 | 55 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| YW Sprints Left | 5
| YW Per Sprint Contribution: | 51.8 | Progress from the Original Estimates, including Scope Changes | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 574 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 3 Sprint Rolling Avg Contribution Projection: | 2018-10-01 | This trend line is based on your most recent contribution. If you maintain that same level of contribution going forward, this line shows where you will deliver. | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 259 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Rolling 3 Sprints Left: | 5 | Velocity Marker | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 325 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Rolling 3 Per Sprint Contribution: | 51.8
| Total Average Contribution Projection: | 2018-10-01 | Zone | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Average Sprints Left: | 5 | Zone Marker | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total Average Per Sprint Contribution: | 51.8
| Original Goal Date: | 2018-10-01
| Goal Per Sprint Contribution: | 52
| Min Sprints: | 20
| Min Per Sprint Contribution: | 65
| Max Sprints: | 30
| Max Per Sprint Contribution: | 43.3333
| Velocity Sprints: | 20
| Sprint Duration | 20

## Projector
|  |  | Sub - (Sept) Release Burndown Chart |  | #N/A
Select Which Projections to Graph:
Full Velocity Focus: |  | Show | TRUE | scShowOrig
Original Target Projected Range: |  | Show | TRUE | scOTProj
| 3-Sprint Rolling Average: | Show | TRUE | scShow3RCon
| Total Average: | Show | TRUE | scShowTACon
| Yesterday's Weather: | Show | TRUE | scShowYWCon
Velocity-Based | 3-Sprint Rolling Average: | Hide | FALSE | scShow3RVel
| Total Average: | Hide | FALSE | scShowTAVel
| Yesterday's Weather: | Hide | FALSE | scShowYWVel
Notes: