## Slide 1
Progress Update: Connected Samurai (HXF)
Project Lead | Primary Contact | Status Date
Rock Mutchler | Lakshmi M | 07/10/18
TEAM Goal: Connected Technologies Platform - “Create awesome customer experience for connected technologies offered to Toyota and Lexus customer” - Primarily responsible for the Cross functional activities supporting CY 17 + App teams
Top achievements since last status report: (06/26/18) – CTP Sprints 11,12
Completed the Pilot Onboard – Zuora, Products and OCPR
Completed the Corresponding CTP Tools and Pipelines
Completed the Service Decomposition and Refactoring for Pilot Services
Completed the PoC for Geo Location and Route 53 Load Balancing for CTP DEV
Completed Demo of ALB and Task Definitions via TF for CTP - Scaling
Completed JWT Token Validation for S2S Only using Spring Security
Completed JFrog X-ray Integration to CTP via Jenkins
Completed Locust IO POC and How to Guideline for Perf Testing Automation
Completed Sonar Rules configuration for use to CTP Onboard for Apps
Completed Locust Integration to CTP Dev Pipeline
Completed SSM Migration via Pipeline to Artifactory for Secrets Mgmt.
Planned Pipeline for Next Report:
Complete Service Discovery configuration for Spring framework using Route 53 on AWS for CTP
Complete Onboarding Subscription services – Orch Subscription, Zuora-Service, Subscription Mgmt.
Complete Onboarding Vehicle Mgmt Services – Vehicle Details, ADF, FDF (Receiver)
Complete XLR Set up for the CTP Pipeline QA with XLR inputs
Refactor Terraform VPC for scaling services for CD
Migrate TC Log util to CTP for Registration Apps – Decouple TC
Create Jenkins back up snap shot for Instance Outages
Service decomposition for App Onboarding – Sprint Efforts
Quick references: Confluence/ Bit Bucket
https://confluence.sdlc.toyota.com/display/CTP/CTP+Pipeline+-+Tools+and+Workflow+for+Onboard+-+Registration+Apps
https://confluence.sdlc.toyota.com/pages/viewpage.action?pageId=112929199
https://confluence.sdlc.toyota.com/display/CTP/How+To+Guideline+for+Performance+Automation+testing+-+Locust.IO
https://confluence.sdlc.toyota.com/pages/viewpage.action?pageId=111248765
https://confluence.sdlc.toyota.com/display/CTP/CTP+Subnets+and+Jump+Box+-+Bastion+hosts
https://bitbucket.sdlc.toyota.com/projects/CTP (Code !!!)
Issue/Risk | Description | Issue Owner | Criticality | Issue Date | Target Date | Status
Action 1 | CTP Pilot OnBoard | Connected Samurai | MED | 062518 | 070218 | Completed the Pilot services CTP DEV Onboard *HIGH*
Action 2 | Performance Testing | Connected Samurai | HIGH | 070218 | 073018 | Completed the tool analysis for Locust IO and Outreached for Automation scripting for Service API’s – IN PROGRESS
Action 3 | CTP Pipeline for Registration Apps | Connected Samurai | HIGH | 070918 | 081018 | On Target – Onboard all the Registration App services/ Repos from TC Pipeline to CTP on CT - * High*
Artifacts:
JIRA  https://jira.sdlc.toyota.com/secure/RapidBoard.jspa?rapidView=2552
Bitbucket  https://bitbucket.sdlc.toyota.com/projects/CTP
Confluence  https://confluence.sdlc.toyota.com/display/CTP/Connected+Technology+Platform+-+HOME
Decision | Refactor Code with App Teams for CTP Onboard | Connected Samurai | HIGH | 070918 | 081018 | All of Registration Apps – Need collaboration with CTP per CPO Request to Migrate all of the Services/ Repo from TC to CTP