## Registration Services to CTP
Migration of Registration Apps to CTP AWS Platform (Final Cut Off Date - 08/10/2018)
Application Name | Migration Date | Build Ever Done in TC - YES/ NO | Current Status | Action Item For | Comments
CTP AWS Platform
CICD platform pipeline readiness | 2018-07-06 | NO | Completed | HXF | Pipeline readiness - CTP DEV
Deployment pipeline - ECS platform | 2018-07-06 | NO | Completed | HXF | Platform readiness - CTP DEV
Service decomposition and refactoring pilot services - Without Log Util | 2018-07-06 | NO | Completed | HXF | Completed and Demo'ed the Pilot services for OCPR, Zuora and Products - Subscription
Subscription Services (Total number of services 5 - Identified)
ctp-orch-subscription | 2018-07-16 | YES | In Progress | AppTeam/HXF
ctp-zuora-service | 2018-07-16 | YES | In Progress | AppTeam/HXF
ctp-subscription | 2018-07-16 | YES | In Progress | AppTeam/HXF
ctp-provisioning | 2018-07-23 | YES | Planned | AppTeam/HXF
ctp-products | 2018-07-23 | NO | Planned | AppTeam/HXF
admintool |  | YES |  | AppTeam/HXF
tarp-plus-web |  | YES |  | AppTeam/HXF
subscriptionRepo |  | NO |  | AppTeam/HXF
orch-vin-association |  | YES |  | AppTeam/HXF
Vehicle Management Services
ctp-adf-receiver | 2018-07-16 | NO | In Progress | AppTeam/HXF
ctp-fdf-receiver | 2018-07-16 | NO | In Progress | AppTeam/HXF
ctp-vehicle-details | 2018-07-16 | NO | In Progress | AppTeam/HXF
consolidated-vehicle-store -Including CORE | 2018-07-16 | YES | In Progress | AppTeam/HXF
svpp |  | NO |  | AppTeam/HXF
orch-cvs |  | YES |  | AppTeam/HXF
Account Management Services
ctp-ocpr | 2018-07-16 | YES | In Progress | AppTeam/HXF
orch-get-customer-details |  | YES |  | AppTeam/HXF
One App services
Oneapp-Android |  | NO |  | AppTeam/HXF
Orch-remote |  | NO |  | AppTeam/HXF
Onepp-iOS |  | NO |  | AppTeam/HXF
Unknown repos
automation-registration |  | NO |  | AppTeam/HXF
devops-blueprint |  | NO |  | AppTeam/HXF
security-util |  | NO |  | AppTeam/HXF
provisioning-automation-selenium-testing |  | NO |  | AppTeam/HXF
generate-subscription-feature-files |  | NO |  | AppTeam/HXF
provisioning-automation-api-testing |  | NO |  | AppTeam/HXF
orch-provisioning |  | NO |  | AppTeam/HXF
orchestration |  | YES |  | AppTeam/HXF
Collector |  | NO |  | AppTeam/HXF